## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2225-swen-261-06-g RIT Garage Sale
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. |  |  | Pass | JK; 4/4
| Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. |  |  | Pass | JK; 4/4
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. |  |  | Pass | JK; 4/5
| Given that I am on the products page when there are products in the inventory then I see each product and short description. |  |  | Pass | JK; 4/4
| Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart. |  |  | Pass | JK; 4/4
As a DEVELOPER I want to go to the website so that I can see a template for development purposes. | Given I am using a valid web browser when navigate to the website then I expect to see a default page. |  | JK; 3/21/23; The default page is visible using firefox. | Pass | JK; 4/4
As a User I want to see the homepage so that I can navigate the site. | Given I have a working web browser when I go to the site url then I expect the store home page. |  | JK; 3/21/23; The store home page is visible using firefox. | Pass | JK; 4/4
As a User I want to See a list of all products so that I can decide what to buy. | Given I am on the dashboard when I navigate to the product list then I expect to see all products. |  | JK; 3/21/23; The product list of all products in the JSON file is visible and accessible from the dashboard. | Pass | JK; 4/4
As a User I want to see product details so that I can choose what to buy. As an Admin I want to see product details so that I can edit product information | Given I am on the product list or dashboard when I click a product then I want to see or edit product information. |  | JK; 3/21/23; The website brings me to a pop up where I can see and edite product information after I click on a product. | Pass | JK; 4/4
As a Buyer, I want to remove products from my cart so that I don't purchase what I don't want. | Given I am a customer when remove a product in my cart then I expect that item to be removed from my shopping cart. |  | JK; 3/21/23; It does remove it from the backend, and I can do that in the frontend | Pass | JK; 4/4
As a admin I want to be able to see message reports for commands that I enter so that I can debug the website. | Given I am an admin with the message service turned on when I enter perform a website supported command then I expect to see that command in the message display. |  | AB; 3/21/23; The message service is only visible when logged in as the admin | Pass | JK; 4/4
As a buyer I want to be able to edit the quantities of products in my cart so that I don’t have to add each individually. | Given I am a customer when I request to increase the quantity of a product in my shopping cart then I expect the quantity to increase. |  | JK; 3/21/23; This does work in the backend, and in the frontend | Pass | JK; 4/4
| Given I am a customer when I request to decrease the quantity of a product in my shopping cart then I expect the quantity to decrease. |  | JK; 3/21/23; This does work in the backend and the front | Pass | JK; 4/4
As a Buyer, I want to add products to my cart so that I can save them for later and to purchase them all at once. | Given I am a customer when I add a product then I expect that item to be saved to my shopping cart. |  | JK; 3/21/23; Backend representation works, and the front end represents it | Pass | JK; 4/4
As a customer I want to be able to create an account so that I can purchase products and ensure my shopping cart is persistent. | Given I am on the account creation page when I enter an available account username and press create then I expect an account with that name to be created for me. |  | JK;3/21/23; Backend working for this, and can do it from the frontend | Pass | JK; 4/4
As an customer I want to be able to login & logout of the E-store so that I can verify my identity to browse and purchase products. | Given that I have correct customer credentials when I enter them into the login field then I expect to be logged in as myself, a customer. |  | AB; 3/21/23; Customers can log in as themselves using their customer login. | Pass | JK; 4/4
As an admin I want to be able to login & logout of the E-store so that I can verify my identity to perform restricted actions such as adding and removing products. | Given that I have correct admin credentials when I enter them into the login field then I expect to be logged in as an admin. |  | AB; 3/21/23; The admin can log in as themselves using the admin login. | Pass | JK; 4/4
As a buyer I want to view and use my cart so that I can view the items in it. | Given I am a customer when I press view my cart then I expect to see my shopping cart |  | AB; 3/21/23; The customers can see their persistent shopping cart. | Pass | JK; 4/4
As a User I want to see the product in my cart match the store so that I pay the appropriate amount, and get the number of products I am expecting | **Given** there is a product in my cart **when** I log in **then** the product in my cart should remove itself if the product was removed from the store. |  |  | Pass | JK; 4/4
| **Given** there is a product in my cart **when** I log in **then** the product in the cart should clamp its quantity to be at most the number in stock in the store |  |  | Pass | JK; 4/4
| **Given** there is a product in my cart **when** I log in **then** the product in the cart should update the price to match the store |  |  | Pass | JK; 4/4
As a developer I want to remove all products from a cart so that purchasing a cart can be reflected. | Given A cart has products when delete all products is called then all product objects in that cart should be removed. |  |  | Pass | JK; 4/4
As a USER when I press ADD TO CART it should ADD 1 TO MY CART IF PRODUCT IS ALREADY THERE | Given CART ALREADY HAS A PRODUCT when I ADD THAT PRODUCT then THE QUANTITY IN MY CART INCREASES |  |  | Pass | JK; 4/4
As a USER I want to ONLY ADD AS MUCH TO THE CART AS THERE IS QUANTITY so that I PURCHASE THE CORRECT NUMBER OF PRODUCTS. | Given There are the same number of a product in my cart as there are in stock when I attempt to add another of that product then no more products should be added. |  |  | Pass | JK; 4/5
As a customer I want to be able to purchase the products in my shopping cart so that I can utilize the E-store. | Given I am a customer with items in my shopping cart when I go to the check out page and enter my details and press checkout then I expect to purchase those items. |  |  | Pass | JK; 4/4
As a user I want to be able to check out products that are in my shopping cart so that I can purchase them. | Given I am a user when I go to check out an item in my shopping cart then I expect it to be removed from my cart (purchased). |  |  | Pass | JK; 4/4
As a Buyer I want to be able to view auction items so that I can bid on items | Given I am on the landing page whenI click the auction house button thenI should go to the auction house page. |  |  | Pass | JK; 4/4
| Given I am on the auction house page when I look at the page then I should see the current item on auction. |  |  | Pass | JK; 4/5
As an admin I want to be able to make auction items so that I can auction out items. | **Given** I am an admin **when** the request is submitted to create an auction **then** I expect an auction to be created on the E-store. |  |  | Pass | JK; 4/5
| **Given** I am an admin **when** the request to delete an auction is issued **then** I expect the auction to be removed from the E-store. |  |  | Pass | JK; 4/5
As a E-store customer I want to see the countdown for an auction of a product so that I can bid on it before it ends. | Given I am a customer when I am viewing an auction then I expect to see a countdown timer for when the auction will end. |  |  | Pass | JK; 4/5
As a user I want to see an organized UI so that I can adequately use the store. | Given I am a user when I visit the e-store then I expect to see a usable and organized UI |  |  | Pass | JK; 4/4
As an E-store user I want to be able to my credentials stored in a database so that I can log in and access my account whenever I want. | Given I am an E-store user when I plug in the right credentials to the login page then I expect to access my account. |  |  | Pass | JK; 4/4
As a customer I want to have the E-store's products I want to purchase saved in a database so that they are persistent across multiple sessions. | Given I am a user when I access the E-store then I expect to be able to access the items in my shopping cart across sessions. |  |  | Pass | JK; 4/4
As a user I want access to the products in the E-store's inventory stored in a database so that they can be utilized. | Given I have admin access when I add an item to the inventory then I expect it to be contained in the database. |  |  | Fail | JK; 4/4
| Given I have admin access when I remove an item from the inventory then I expect it to be removed from the database. |  |  | Fail | JK; 4/4; Feature Scrapped
| Given I am a user when I access the E-store then I expect to see the inventory items contained in the database. |  |  | Fail | JK; 4/4; Feature Scrapped