## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2225-swen-261-06-g RIT Garage Sale
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a DEVELOPER I want to go to the website so that I can see a template for development purposes. | Given I am using a valid web browser when navigate to the website then I expect to see a default page. | Pass | JK; 3/21/23; The default page is visible using firefox.
As a User I want to see the homepage so that I can navigate the site. | Given I have a working web browser when I go to the site url then I expect the store home page. | Pass | JK; 3/21/23; The store home page is visible using firefox.
As a User I want to See a list of all products so that I can decide what to buy. | Given I am on the dashboard when I navigate to the product list then I expect to see all products. | Pass | JK; 3/21/23; The product list of all products in the JSON file is visible and accessible from the dashboard.
As a User I want to see product details so that I can choose what to buy. As an Admin I want to see product details so that I can edit product information | Given I am on the product list or dashboard when I click a product then I want to see or edit product information. | Pass | JK; 3/21/23; The website brings me to a pop up where I can see and edite product information after I click on a product.
As a Buyer, I want to remove products from my cart so that I don't purchase what I don't want. | Given I am a customer when remove a product in my cart then I expect that item to be removed from my shopping cart. | Pass | JK; 3/21/23; It does remove it from the backend, and I can do that in the frontend
As a admin I want to be able to see message reports for commands that I enter so that I can debug the website. | Given I am an admin with the message service turned on when I enter perform a website supported command then I expect to see that command in the message display. | Pass | AB; 3/21/23; The message service is only visible when logged in as the admin
As a buyer I want to be able to edit the quantities of products in my cart so that I don’t have to add each individually. | Given I am a customer when I request to increase the quantity of a product in my shopping cart then I expect the quantity to increase. | Pass | JK; 3/21/23; This does work in the backend, and in the frontend
| Given I am a customer when I request to decrease the quantity of a product in my shopping cart then I expect the quantity to decrease. | Pass | JK; 3/21/23; This does work in the backend and the front
As a Buyer, I want to add products to my cart so that I can save them for later and to purchase them all at once. | Given I am a customer when I add a product then I expect that item to be saved to my shopping cart. | Pass | JK; 3/21/23; Backend representation works, and the front end represents it
As a customer I want to be able to create an account so that I can purchase products and ensure my shopping cart is persistent. | Given I am on the account creation page when I enter an available account username and press create then I expect an account with that name to be created for me. | Pass | JK;3/21/23; Backend working for this, and can do it from the frontend
As an customer I want to be able to login & logout of the E-store so that I can verify my identity to browse and purchase products. | Given that I have correct customer credentials when I enter them into the login field then I expect to be logged in as myself, a customer. | Pass | AB; 3/21/23; Customers can log in as themselves using their customer login.
As an admin I want to be able to login & logout of the E-store so that I can verify my identity to perform restricted actions such as adding and removing products. | Given that I have correct admin credentials when I enter them into the login field then I expect to be logged in as an admin. | Pass | AB; 3/21/23; The admin can log in as themselves using the admin login.
As a buyer I want to view and use my cart so that I can view the items in it. | Given I am a customer when I press view my cart then I expect to see my shopping cart | Pass | AB; 3/21/23; The customers can see their persistent shopping cart.